Date issued: 16th of July 2025

Freedom of Information Request 171/25

You asked us…

I’d like to understand the background to the improvement works around Treherbert Railway Station and the footpath running alongside it and Station Terrace.

Work to improve the path has been promised by TFW and RCTCBC during consultation for the electrification works and this has not been finished with no sign of it being done. The footpath is in a total state of disrepair and is dangerous for residents and station users, worsened by TFW works with debris and temporary fencing left to the front of properties.

I want to understand who has ownership of these unfinished works and when they are to be completed.

RESPONSE

Stations and Sidings Area

- Sidings Lighting - This work is scheduled for completion by 28th August 2025.

- Final Drainage Connection - The drainage connection has now received full approval under Sections 104 and 106. A Temporary Traffic Regulation Order (TTRO) has been requested to facilitate the works. Subject to confirmation of the TTRO, work is planned to commence on 1st September 2025, with an estimated duration of approximately 4 weeks, targeting completion by 1st October 2025.

Sidings Staff Accommodation –

- New Staff Accommodation Construction, North of the station is due to commence on 31st July, with completion anticipated by 30th April 2026.

New Passenger Waiting Room

- This refurbishment is contingent on the successful relocation of staff into the new accommodation. Works are planned to start on 30th April 2026, with an estimated duration of 4–6 weeks, subject to final design approvals.

We hope this information is of use to you.

Yours sincerely,

Transport for Wales

Appeal Rights

If you are unhappy with the way your request has been handled and wish to make a complaint or request a review of our decision, please write to the Head of Freedom of Information at either Transport for Wales, 3 Llys Cadwyn, Pontypridd, CF37 4TH or freedomofinformation@tfw.wales. Your request must be submitted within 40 working days of receipt of this letter. If you are not content with the outcome of the internal review, you have the right to apply directly to the Information Commissioner for a decision.

The Information Commissioner (ICO) can be contacted at Information Commissioner's Office, Wycliffe House, Water Lane, Wilmslow, Cheshire, SK9 5AF or you can contact the ICO through the 'Make a Complaint' section of their website on this link: https://ico.org.uk/make-a-complaint/

The relevant section to select will be "Official or Public Information".